{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["report"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"report","index":0,"n_rows":363,"n_cols":5,"rows_kept":363,"cut":false,"hidden":false,"merged":[]}
["Building","Room","Proposed Date","Completed*","*Completed Panels have been moved to the bottom of the list. "]
["Airport","Airport Control Tower iStar","TBD"]
[null,"Airport GA Terminal Rm 101 Ultra","TBD"]
[null,"Airport Hanger 3 Vehicle Gate 3 Edge","TBD"]
[null,"Airport Main Terminal iStar A","TBD"]
[null,"Airport Main Terminal iStar B","TBD"]
[null,"Airport Main Terminal iStar C","TBD"]
[null,"Airport Maint Hanger Rm T109A iStar","TBD"]
[null,"Airport T-Hanger Edge","TBD"]
[null,"Airport T-Hanger Man Gate EDGE","TBD"]
["Special Services Bldg","Special Services Bldg Rm T210 Ultra","2020-12-14","X"]
["101 Lubert Bldg","Lubert Rm 213M Ultra","2020-12-14","X"]
["The 103 Building","The 103 Building Rm 214 Ultra","2020-12-14","X"]
["100 Outreach Building","Outreach Rm T105 iStar","2020-12-14","X"]
[null,"Outreach Rm T105 Ultra A","2020-12-14","X"]
[null,"Outreach Rm T105 Ultra B","2020-12-14","X"]
["200 Technology Center Building","Technology Center Rm T106 ULTRA","2020-12-14","X"]
["The 230 Bldg","The 230 Bldg Rm T139 Edge","2020-12-14","X"]
[null,"The 230 Bldg Rm T139 Ultra","2020-12-14","X"]
["The 329 Bldg","The 329 Building Rm T215 iStar A","2020-12-14","X"]
[null,"The 329 Building Rm T215 iStar B","2020-12-14","X"]
["The 331 Bldg","The 331 Building Rm T224 ULTRA","2020-12-14","X"]
[null,"The 331 Building Rm T224 ULTRA Panel B","2020-12-14","X"]
[null,"The 331 Building Rm T316Q iStar","2020-12-14","X"]
["The 328 Bldg","The 328 Building Rm 325 Ultra","2020-12-14","X"]
["The 330 Bldg","The 330 Building Rm 105P iStar","2020-12-14","X"]
["BJC","BJC Rm T051A Edge","2020-12-14","X"]
[null,"BJC Rm T246 Edge","2020-12-14","X"]
[null,"BJC Rm T076 Edge","2020-12-14","X"]
[null,"BJC Rm T076 iStar","2020-12-14","X"]
[null,"BJC Rm T245 iStar","2020-12-14","X"]
[null,"BJC Rm T246 iStar","2020-12-14","X"]
[null,"BJC Rm T303 iStar","2020-12-14","X"]
[null,"BJC Rm T303B-238 Edge","2020-12-14","X"]
["Pegula","Pegula Rm T306 Edge","2020-12-14","X"]
[null,"Pegula Rm T315 Edge","2020-12-14","X"]
[null,"Pegula Rm T109 iStar","2020-12-14","X"]
[null,"Pegula Rm T116 iStar","2020-12-14","X"]
[null,"Pegula Rm T152 iStar","2020-12-14","X"]
[null,"Pegula Rm T165 iStar","2020-12-14","X"]
["Pell Lab","Pell Lab Rm T003 iStar A","2020-12-15","X"]
[null,"Pell Lab Rm T003 iStar B","2020-12-15","X"]
[null,"Pell Lab Rm T003 iStar C","2020-12-15","X"]
[null,"Pell Lab Rm T003 iStar D","2020-12-15","X"]
[null,"Pell Lab Rm T003 iStar E","2020-12-15","X"]
["IM Building","IM Building Rm T005 istar","2020-12-15","X"]
[null,"IM Building Rm T005 iStar Edge","2020-12-15","X"]
[null,"IM Building Rm T020 iStar","2020-12-15","X"]
["Shields Bldg","Shields Rm T113 iStar A","2020-12-15","X"]
[null,"Shields RM T113 Istar Pro C","2020-12-15","X"]
[null,"Shields Rm T113 Ultra B","2020-12-15","X"]
["Wagner","Wagner Rm T317 iStar","2020-12-15","X"]
[null,"Wagner Rm T317 ULTRA B","2020-12-15","X"]
[null,"Wagner Annex Rm 014B ULTRA","2020-12-15","X"]
["Findley Commons","Findlay Commons Rm T105 iStar","2020-12-15","X"]
["Indoor Multi Sport Facility","Indoor Multi-Sport Rm T113 iStar","2020-12-15","X"]
["Forest Research Lab","Forest Research Lab Rm T313 Ultra","2020-12-15","X"]
["Research Bldg D","Research Bldg D Rm T102 iStar","2020-12-15","X"]
[null,"Research Bldg D Rm T102 Ultra","2020-12-15","X"]
["Research Bldg A","Research Unit A Modular RM T105 Ultra","2020-12-15","X"]
["Research Bldg A","Research Unit A Rm T104 Ultra","2020-12-15","X"]
["Research Bldg B","Research Unit B RM T113A Ultra","2020-12-15","X"]
["Research Bldg C","Research Unit C RM T103 Ultra","2020-12-15","X"]
["CBL","Central Bio Lab Rm T142 iStar","2020-12-15","X"]
["Materials Research Lab (MRL)","Materials Res Lab Rm T001 Ultra","2020-12-15","X"]
["Land Water Research","Land Water Research Rm T111 iStar","2020-12-15","X"]
["Transportation Res","Transportation Res Rm T133 iStar","2020-12-15","X"]
["Holuba","Holuba Hall Rm 106 iStar","2020-12-15","X"]
["East Area Locker Room","East Area Lockers Rm T132 iStar","2020-12-15","X"]
["Lasch","Lasch Rm T118 ISTAR","2020-12-15","X"]
["Lasch","Lasch Rm T239 istar","2020-12-15","X"]
["Greenberg","Greenberg Rm T102 iStar","2020-12-16","X"]
["Greenberg","Greenberg Rm T118 iStar","2020-12-16","X"]
["Greenberg","Greenberg Rm T124 iStar","2020-12-16","X"]
["Academic Activates","Academic Activities Rm T206 iStar","2020-12-16","X"]
["Coal Utilization","Coal Utilization Lab Rm T102 iStar","2020-12-16","X"]
["Academic Projects","Academic Projects Rm T213 iStar","2020-12-16","X"]
["Research East","Research East Rm T004 IStar","2020-12-16","X"]
["Technology Support Building","Technology Support Rm T039 iStar","2020-12-16","X"]
["EMS Energy Inst","EMS Energy Inst Rm T120 iStar","2020-12-16","X"]
["The 3058 Bldg","The 3058 Res Dr Rm T206 Ultra","2020-12-16","X"]
["CATO II","CATO Park Annex II Rm 110 Edge","2020-12-16","X"]
["NARCO Bldg","NARCO Building Rm T131 iStar","2020-12-16","X"]
["Science Park Library","Sci Park Lib Annex Rm T108 Ultra","2020-12-16","X"]
["Calder Sq II","Calder Square II Rm 403 Edge","2020-12-16","X"]
["Downtown Theatre","Downtown Theater Rm B037 EDGE","2020-12-16","X"]
[null,"The 224 S Allen Building Edge","2020-12-16","X"]
["Shavers Creek","Shavers Creek Rm T103 Ultra","2020-12-16","X"]
["Erickson Food Science","Erickson Rm T002 iStar A","2020-12-16","X"]
[null,"Erickson Rm T002 Ultra B","2020-12-16","X"]
["Ag Sci","Ag Sci Rm T008A iStar","2020-12-16","X"]
["Ag Admin","Ag Admin Rm 410 iStar","2020-12-16","X"]
[null,"Ag Admin Rm T121 iStar","2020-12-16","X"]
[null,"Forestry Rm T226 Ultra","2020-12-16","X"]
["Business","Business Rm 013 iStar Master","2020-12-17","X"]
[null,"Business Rm 218A iStar Panel A Member","2020-12-17","X"]
[null,"Business Rm 218A iStar Panel B Member","2020-12-17","X"]
[null,"Business Rm 218A iStar Panel C Member","2020-12-17","X"]
[null,"Business Rm T203 iStar Panel A Member","2020-12-17","X"]
[null,"Business Rm T203 iStar Panel B","2020-12-17","X"]
[null,"Business RM T453 iStar","2020-12-17","X"]
[null,"Business Rm T482 iStar","2020-12-17","X"]
[null,"Eisenhower Deck Rm T039 iStar A","2020-12-17","X"]
["Headhouse I","Headhouse I Rm T124 Edge","2020-12-17","X"]
["Headhouse III","Headhouse III Rm T124 Edge","2020-12-17","X"]
["Tyson","Tyson Rm T002 ULTRA","2020-12-17","X"]
["Borland","Borland Rm T015 iStar","2020-12-17","X"]
["Visual Arts","Visual Arts Rm T011 iStar","2020-12-17","X"]
[null,"Visual Arts-Ceramics Rm M001 Ultra","2020-12-17","X"]
["Stuckeman","Stuckeman Rm T146 iStar","2020-12-17","X"]
["Weaver","Weaver Rm T307 iStar","2020-12-17","X"]
["Armsby","Armsby Rm T212A iStar","2020-12-17","X"]
["Patterson","Patterson Rm T401 Ultra","2020-12-17","X"]
["Arts Cottage","Arts Cottage Rm T106 Ultra","2020-12-17","X"]
["Pavilion Theater","Pavilion Theater Rm E004A Ultra","2020-12-17","X"]
["Ferguson","Ferguson Rm T111A Ultra","2020-12-17","X"]
["CBEB","CBEB Rm T219 Ultra A","2020-12-17","X"]
["CBEB","CBEB Rm T219 Ultra B","2020-12-17","X"]
["CBEB","CBEB Rm T219 Ultra C","2020-12-17","X"]
["CBEB","CBEB Rm T219 Ultra D","2020-12-17","X"]
["CBEB","CBEB Rm T419 Ultra A","2020-12-17","X"]
["CBEB","CBEB Rm T419 Ultra B","2020-12-17","X"]
["CBEB","CBEB Rm T419 Ultra C","2020-12-17","X"]
["CBEB","CBEB Rm T419 Ultra D","2020-12-17","X"]
["Ag Analytical","Ag Analytical Rm T117 Ultra","2020-12-17","X"]
["High Pressure Gas Lab","High Pressure Gas Lab Rm P122 Ultra","2020-12-17","X"]
["Blue Band","Blue Band Rm T111 Ultra","2020-12-17","X"]
["Katz Bldg","Katz Rm T103 iStar","2020-12-17","X"]
[null,"Katz Rm T003 iStar","2020-12-17","X"]
[null,"Katz Rm T203 iStar 2nd Flr","2020-12-17","X"]
[null,"Katz Rm T203 iStar 3rd Flr","2020-12-17","X"]
["Arboretum","Arboretum Rm M103 iStar","2020-12-17","X"]
["Supplemental Mail Bldg","Supplemental Mail Rm 104 iStar","2020-12-21","X"]
["USB III","USB III Rm T101 EDGE","2020-12-21","X"]
["Salvage","Procurement Svcs Rm T112 iStar","2020-12-21","X"]
["Hostetter Business","Hostetter Business Svc Rm T106 iStar","2020-12-21","X"]
["Schreyer House","Schreyer House East Mech Rm iStar","2020-12-21","X"]
["CATO I","CATO Park Annex I Rm 001 Edge","2020-12-21","X"]
[null,"CATO Annex I Rm 123 Ultra Palmer Stg","2020-12-21","X"]
["Ag Eng","Ag Eng Rm T237 Ultra","2020-12-21","X"]
["Palmer Museum","Palmer Museum Rm T104 Ultra","2020-12-21","X"]
[null,"Palmer Museum Rm T002 iStar","2020-12-21","X"]
["MSC","MSC Rm NT258 iStar A","2020-12-21","X"]
[null,"MSC Rm WT127 iStar A","2020-12-21","X"]
[null,"MSC Rm WT127 iStar B","2020-12-21","X"]
[null,"MSC RM NT020 iStar A","2020-12-21","X"]
[null,"MSC RM NT020 iStar B","2020-12-21","X"]
[null,"MSC Rm NT152 iStar A","2020-12-21","X"]
[null,"MSC Rm NT152 iStar B","2020-12-21","X"]
[null,"MSC Rm NT258 iStar B","2020-12-21","X"]
[null,"MSC Rm NT347 iStar","2020-12-21","X"]
[null,"MSC Rm WT127 iStar C","2020-12-21","X"]
[null,"MSC Rm WT249 iStar","2020-12-21","X"]
[null,"MSC Rm WT338 iStar","2020-12-21","X"]
["Huck","Huck LSB Rm T310 iStar A","2020-12-21","X"]
[null,"Huck LSB Rm T310 Ultra B","2020-12-21","X"]
[null,"Huck LSB Rm T310 Ultra C","2020-12-21","X"]
["Chemistry","Chemistry Rm P109 Ultra","2020-12-21","X"]
["Computer","Computer Rm T011 Edge","2020-12-22","X"]
["Student health Ctr","Student Health Ctr Rm T364 iStar","2020-12-22","X"]
["Wartik","Wartik Lab Rm T103 Edge","2020-12-22","X"]
[null,"Wartik Lab Rm T202 iStar","2020-12-22","X"]
[null,"Wartik Lab Rm 312 ULTRA","2020-12-22","X"]
[null,"Wartik Lab Rm J201 ULTRA","2020-12-22","X"]
["Pollock","Pollock Building Rm T111 iStar","2020-12-22","X"]
["Bennett","Bennett Rm T110 iStar","2020-12-22","X"]
["Thomas","Thomas Rm T001 iStar","2020-12-22","X"]
[null,"Thomas Rm T020 Aud Edge","2020-12-22","X"]
["Ritenour Rm","Ritenour Rm T024A iStar","2020-12-22","X"]
[null,"Ritenour Rm T028 Ultra","2020-12-22","X"]
["Boucke","Boucke Rm T318 Ultra","2020-12-22","X"]
["Althouse Lab","Althouse Lab Rm T010 iStar","2020-12-22","X"]
["Mueller Rm","Mueller Rm T103 iStar A","2020-12-22","X"]
[null,"Mueller Rm T103 iStar B","2020-12-22","X"]
[null,"Mueller Rm T103 iStar C","2020-12-22","X"]
["Beaver Stadium","Beaver Stadium Rm 01-403-07 EMS iStar","2021-01-04","X"]
[null,"Beaver Stadium Rm 01-901-44A PD iStar","2021-01-04","X"]
[null,"Beaver Stadium Rm T01-901-50 iStar","2021-01-04","X"]
[null,"Beaver Stadium Rm T09-502-05 iStar","2021-01-04","X"]
[null,"Beaver Stadium T01-300-01 Edge","2021-01-04","X"]
[null,"Beaver Stadium Rm T01-603-04 Edge","2021-01-04","X"]
[null,"Beaver Stadium Rm T01-802-01 iStar Telcom A","2021-01-04","X"]
[null,"Beaver Stadium T08-603-02 Edge","2021-01-04","X"]
["Buckhout","Buckhout Rm T215A iStar","2021-01-04","X"]
["Bank of America","Bank Of America Rm T003 iStar","2021-01-04","X"]
["Frear North","Frear North Rm T166 iStar","2021-01-04","X"]
["Frear South","Frear South Rm T110 iStar A","2021-01-04","X"]
[null,"Frear South Rm T110 iStar B","2021-01-04","X"]
["Whitmore Rm","Whitmore Rm T006 iStar A","2021-01-04","X"]
[null,"Whitmore Rm T006 iStar B","2021-01-04","X"]
["Osmond","Osmond Lab RmT010 Edge","2021-01-04","X"]
["Davey Lab","Davey Lab Rm T028 iStar","2021-01-04","X"]
[null,"Davey Lab Rm T522 iStar","2021-01-04","X"]
["Chandlee Lab","Chandlee Lab Rm T326 iStar","2021-01-04","X"]
["Schwab","Schwab Rm T013 iStar","2021-01-04","X"]
["Old Main","Old Main Rm T001 Ultra","2021-01-04","X"]
["McAllister","McAllister RM T011 iStar","2021-01-04","X"]
["HUB-Robeson","HUB-Robeson Rm T131 iStar","2021-01-04","X"]
[null,"HUB-Robeson Rm T240 iStar A","2021-01-04","X"]
[null,"HUB-Robeson Rm T240 iStar B","2021-01-04","X"]
[null,"HUB-Robeson Rm T240 iStar C","2021-01-04","X"]
[null,"HUB-Robeson Rm TB012 iStar","2021-01-04","X"]
["Grange","Grange Rm T019 iStar","2021-01-04","X"]
["White","White Rm T133 iStar","2021-01-04","X"]
["BioBehavior","BioBehavior Rm T217 iStar","2021-01-04","X"]
["Henderson","Henderson Rm T011 Ultra","2021-01-04","X"]
["Nittany Lion Inn","Nittany Lion Inn Rm T2093 iStar","2021-01-05","X"]
["Health Human Dev","Health Human Dev Rm T346 iStar","2021-01-05","X"]
["Nursing Science","Nursing Science Rm T213 iStar","2021-01-05","X"]
["Ford Building","Ford Building Rm T015 Ultra","2021-01-05","X"]
["Theatre Building","Theatre Building Rm T131 iStar","2021-01-05","X"]
[null,"Theatre Building Rm T131 iSTAR Ultra B","2021-01-05","X"]
["Music II","Music II Rm T053 iStar","2021-01-05","X"]
[null,"Music II Rm T053 iSTAR Ultra B","2021-01-05","X"]
["Music I","Music I Rm T201 Ultra A","2021-01-05","X"]
["Eisenhower Chapel","Eisenhower Chapel Rm T006 iStar","2021-01-05","X"]
["Chambers","Chambers Rm T175 Ultra","2021-01-05","X"]
[null,"Chambers Rm T237 iStar A","2021-01-05","X"]
[null,"Chambers Rm T237 iSTAR B","2021-01-05","X"]
["CEDAR","CEDAR Rm T002 iStar A","2021-01-05","X"]
[null,"CEDAR Rm T002 Ultra B","2021-01-05","X"]
[null,"CEDAR Rm T002 Ultra C","2021-01-05","X"]
["Moore Building","Moore Building Rm T017 Edge","2021-01-05","X"]
[null,"Moore Building Rm T365 iStar A","2021-01-05","X"]
[null,"Moore Building Rm T365 iStar B","2021-01-05","X"]
["Mateer","Mateer Rm T106 Ultra","2021-01-05","X"]
["Keller","Keller Rm 212 ULTRA","2021-01-05","X"]
[null,"Keller Rm T214 Edge","2021-01-05","X"]
[null,"Keller RM T214 Ultra","2021-01-05","X"]
["Rackley","Rackley Rm T002 iStar","2021-01-05","X"]
["Kern","Kern RM T003 iStar","2021-01-05","X"]
[null,"Kern Rm T414 iStar","2021-01-05","X"]
["Carpenter","Carpenter Rm T005 Ultra","2021-01-05","X"]
["Marriott Bldg (OAK Bldg)","Oak Building Rm T110 Ultra SE","2021-01-05","X"]
["Paterno Library","Paterno Rm E003A DLT iStar","2021-01-05","X"]
[null,"Paterno Rm ET024 iStar","2021-01-05","X"]
["Pattee Library","Pattee Rm WT003 Ultra SE","2021-01-05","X"]
[null,"Pattee Rm WT025 Ultra","2021-01-05","X"]
["Paterno Bldg","Paterno Rm ET023 iStar","2021-01-05","X"]
["Pattee Bldg","Pattee Rm WT003 iStar","2021-01-05","X"]
["Hintz Rm Bldg","Hintz Rm T005 iStar A","2021-01-05","X"]
[null,"Hintz Rm T005 iStar B","2021-01-05","X"]
["Ihlseng Cottage","Ihlseng Cottage Rm T004 Ultra","2021-01-06","X"]
["Sparks Bldg","Sparks Rm T004 iStar B","2021-01-06","X"]
[null,"Sparks Rm T004 iStar A","2021-01-06","X"]
["Burrowes Bldg","Burrowes Rm T001 Core iStar Master","2021-01-06","X"]
[null,"Burrowes Rm T041 North iStar Member","2021-01-06","X"]
[null,"Burrowes South Rm T007 iStar Member","2021-01-06","X"]
["Oswald Bldg","Oswald Rm T02 iStar","2021-01-06","X"]
["Pond Lab","Pond Lab Rm T119 ULTRA","2021-01-06","X"]
["Carnegie Bldg","Carnegie Rm T114 iStar","2021-01-06","X"]
[null,"Carnegie Rm 225 Ultra","2021-01-06","X"]
["Willard Bldg","Willard Rm TB003 iStar","2021-01-06","X"]
["Steidle Bldg","Steidle Rm T221 iStar A","2021-01-06","X"]
[null,"Steidle Rm T221 iStar B","2021-01-06","X"]
[null,"Steidle Rm T221 iStar C","2021-01-06","X"]
["Hosler Bldg","Hosler Rm T211 Ultra","2021-01-06","X"]
["Deike Bldg","Deike Rm 009 Ultra","2021-01-06","X"]
[null,"Deike Rm T327 iStar","2021-01-06","X"]
["EE West Bldg","EE West Rm T222 iStar A","2021-01-06","X"]
[null,"EE West Rm T222 iStar B","2021-01-06","X"]
["EE East Bldg","EE East Rm T105 iStar","2021-01-06","X"]
["Rider House Bldg","Rider House RM 002 Storage Edge","2021-01-06","X"]
["Elliott Rm Bldg","Elliott Rm T515 iStar A","2021-01-06","X"]
[null,"Elliott Rm T515 iStar B","2021-01-06","X"]
["Rider Bldg","Rider Rm T201 Edge","2021-01-06","X"]
[null,"Rider Rm T403 iStar","2021-01-06","X"]
["Reber Bldg","Reber Rm T220 iStar","2021-01-07","X"]
[null,"Reber Rm T220 Edge","2021-01-07","X"]
["Engineering Unit B Bldg","Engineering Unit B Rm T213 iStar","2021-01-07","X"]
[null,"Engineering Unit B Rm T213 Ultra B","2021-01-07","X"]
["Sackett Bldg","Sackett Rm T321 iStar","2021-01-07","X"]
[null,"Sackett Rm T321 Ultra B","2021-01-07","X"]
["Hammond Bldg","Hammond Rm T211 iStar A","2021-01-07","X"]
[null,"Hammond Rm T211 iStar B","2021-01-07","X"]
[null,"Hammond Rm T223 iStar A","2021-01-07","X"]
[null,"Hammond Rm T223 iStar B","2021-01-07","X"]
["Rider Bldg","Rider Elev Equip Rm M003 iStar","2021-01-07","X"]
["Walker Bldg","Walker Rm T223 Edge","2021-01-07","X"]
[null,"Walker Building Rm T223 iStar","2021-01-07","X"]
[null,"Walker Building Rm T223 ULTRA","2021-01-07","X"]
["Westgate Bldg","Westgate Rm E159X Ultra A","2021-01-07","X"]
[null,"Westgate Rm E159X ULTRA B","2021-01-07","X"]
[null,"Westgate Rm E362 2 ULTRA","2021-01-07","X"]
[null,"Westgate Rm E362 Closet 1 iStar","2021-01-07","X"]
[null,"Westgate Rm ET318 iSTAR Ultra","2021-01-07","X"]
[null,"Westgate Rm W130B ULTRA A MASTER","2021-01-07","X"]
[null,"Westgate Rm W130B ULTRA B","2021-01-07","X"]
[null,"Westgate Rm W362 West Closet ULTRA","2021-01-07","X"]
[null,"Westgate Rm WT121 iStar","2021-01-07","X"]
["Telecomm","Telecomm Video Rm 015 ULTRA","2021-01-07","X"]
["Telecom Bldg","Telecom Video Room 015 EDGE","2021-01-07","X"]
["Merkle Lab","Merkle Lab Rm T109 Edge","2021-01-07","X"]
["Noll Lab Bldg","Noll Lab Rm T130 iStar","2021-01-11","X"]
["Rec Hall Bldg","Rec Hall Rm P060 Ultra","2021-01-11","X"]
[null,"Rec Hall Rm T118 iStar","2021-01-11","X"]
[null,"Rec Hall RM T265 iStar B","2021-01-11","X"]
[null,"Rec Hall RM T265 iStar A","2021-01-11","X"]
["Research West Bldg","Research West Rm T014 iStar A","2021-01-11","X"]
[null,"Research West Rm T014 iStar B","2021-01-11","X"]
[null,"Research West Rm T014 iStar C","2021-01-11","X"]
[null,"Research West Rm T014 Edge","2021-01-11","X"]
["Leonhard Bldg","Leonhard Rm T111 Ultra","2021-01-11","X"]
[null,"Leonhard Rm T223 Ultra","2021-01-11","X"]
["Eng Svc Bldg","Eng Svc Rm T111 iStar","2021-01-11","X"]
["EES Bldg","EES Rm 401 Edge","2021-01-11","X"]
[null,"EES Rm T113 iStar","2021-01-11","X"]
["Fox Hollow Buidling","Fox Hollow Rm T110 iStar","2021-01-11","X"]
["Penn Stater","Penn Stater Rm T101B iStar","2021-01-11","X"]
["Daybridge","Daybridge Rm T031 Ultra","2021-01-11","X"]
["Animal Diagnostic Lab","Animal Diagnostic Lab Rm T021 Edge","2021-01-11","X"]
["Wiley Lab","Wiley Lab Rm 114M iStar","2021-01-11","X"]
["Central Milk Testing","Central Milk Testing Rm T114 iStar","2021-01-11","X"]
["Scent Mediated Eco Lab","Scent Mediated Eco Lab Rm M101 EDGE","2021-01-11","X"]
["Insectary","Insectary Rm F101 Closet iStar","2021-01-11","X"]
["Chemical Ecology Lab","Chemical Ecology Lab Rm T017 Ultra","2021-01-11","X"]
["Visitor Center","Centre Cnty Visitor Center Rm T002 Ultra","2021-01-11","X"]
["Meats Lab","Meats Lab RM T201 IStar","2021-01-11","X"]
["Medlar Field","Medlar Field P126 iStar","2021-01-11","X"]
["Laundry Bldg","Laundry Bldg Rm T205 Edge","2021-01-11","X"]
["Hallowell ","Hallowell Rm T402 Ultra ","2021-01-11","X"]
["Water Treatment #1","Water Treatment 1 ULTRA","2021-01-12","X"]
["Fleet","Fleet Operations Rm T008 Ultra","2021-01-12","X"]
["Physical Plant","Physical Plant Rm T163 iStar","2021-01-12","X"]
[null,"Physical Plant Rm T189 Edge","2021-01-12","X"]
[null,"Physical Plant Rm 160B Ultra B","2021-01-12","X"]
[null,"Physical Plant Rm 160B iStar A","2021-01-12","X"]
[null,"Physical Plant Annex Rm T268 iStar","2021-01-12","X"]
["USB II","USB II Rm T106 Edge","2021-01-12","X"]
[null,"USB II Rm T106 ULTRA","2021-01-12","X"]
[null,"USB II Rm T112L istar","2021-01-12","X"]
[null,"USB II Rm T112L Edge","2021-01-12","X"]
["University Press","University Press Dist Cntr T101 Edge","2021-01-12","X"]
["Tower Road Landscape","Tower Rd Landscape Rm T104A Ultra","2021-01-12","X"]
["OPP Greenhouse","OPP Greenhouse RM P103 Ultra","2021-01-12","X"]
["Water Treatment #2","Water Treatment 2 Rm T206 iStar","2021-01-12","X"]
["HazMat","Hazmat Rm T101 Ultra","2021-01-12","X"]
["College Heights","College Heights Rm TB004 Ultra","2021-01-12","X"]
["Nittany Lion Softball Park","Nittany Lion SB Park Rm T209 iStar","2021-01-12","X"]
["McCoy","McCoy Natatorium Rm M110 iStar","2021-01-12","X"]
[null,"McCoy Natatorium RM S002 iStar","2021-01-12","X"]
["Sarni","Sarni Tennis FAC Rm M001 Mech Edge","2021-01-12","X"]
["Tennis Court Bldg","Tennis Court Building Rm 102 EDGE","2021-01-12","X"]
["Panzer Stadium","Panzer Stadium Rm T104 Ultra","2021-01-12","X"]
["Dairy Admin Bldg","Dairy Admin Bldg Rm 101 Ultra","2021-01-12","X"]
["USB I","USB I Rm T101 iStar","2021-01-12","X"]
[null,"USB I Rm T101 UPPS Edge","2021-01-12","X"]
["Solar House","Solar House Rm 104 Mech EDGE","2021-01-13","X"]
["Swine Research Bldg","Swine Research Rm T201 Edge","2021-01-13","X"]
["East Campus Steam Plant","ECSP Rm 102 iStar","2021-01-13","X"]
["Tombros Golf Clubhouse","Tombros Clubhouse Rm M001 iStar","2021-01-13","X"]
["North Campus Chiller","North Campus Chiller Rm T101 iStar","2021-01-13","X"]
["Ag Chiller","Ag Chiller Building Edge Rm","2021-01-13","X"]
["Hort Woods","Hort Woods Rm T003 iStar","2021-01-13","X"]
["Nittany Parking Deck","Nittany Parking Deck Rm T106 iStar","2021-01-13","X"]
["Steam Svc Bldg","Steam Svc Bldg Rm T003 Ultra A","2021-01-13","X"]
[null,"Steam Svc Bldg Rm T003 Ultra B","2021-01-13","X"]
["West Campus Chiller Bldg","West Campus Chiller Room T101 IStar","2021-01-13","X"]
["Mushroom Research","Mushroom Research Center Rm P124 Ultra","2021-01-13","X"]
["Farm House","Farm House 10 Rm T106 Edge","2021-01-19","X"]
["116 W. College","116 W College Ultra - Scott Bld","2021-01-19","X"]
["Eisenhower Aud","Eisenhower Aud Rm BT012 Edge","2021-01-19","X"]
["Marion Place","Marion Place Rm T404 Edge","2021-01-25","X"]